## Sheet1
S. no. | Issue | Date Reported | Raised By | Status
1 | Insert space between PAN and NO and Adahar and Card and NO | 2017-04-06 | Ananya
2 | Territory is blank in license data | 2017-04-06 | Ananya
3 | First impression within date is only captured partially and the format is different | 2017-04-06 | Ananya
4 | SAP numbers not entered although provided in Data sheet | 2017-04-06 | Ananya
5 | Other Contracts INSTEAD by executive – Please change to ISSUED | 2017-04-06 | Ananya
6 | Other Contracts – Please change Free Lancer to Freelancer | 2017-04-06 | Ananya
7 | Other contracts - 2 upload options – once while creating the contract and once while updating details. Upload option while entering Other Contract details is not required | 2017-04-06 | Ananya
8 | Revised Series Data shared | 2017-04-06 | Ananya
9 | Correction to InBound permissions data sheet done and entered | 2017-04-06 | Ananya
10 | Linking to Previous ISBN - Done with NO instead of Yes | 2017-05-05 | Ananya
11 | Production Data not uploaded | 2017-05-08 | Ananya
12 | ISBN Bin - segregated as Print and CD, Computer software, digital etc. Asked to club all components of Digital under one head i.e. digital | 2017-05-08 | Ananya
13 | ISBN bin - Sample file download showing 404 error | 2017-05-08 | Ananya
14 | Delete Product option in admin log not working | 2017-05-09 | Ananya
15 | Other contract upload is not working | 2017-05-09 | Ananya
16 | Domain Name - Not secure | 2017-05-09 | Ananya
17 | Domain Name - URL issue | 2017-05-09 | Ananya
18 | ISBN Bin - Upload disabled | 2017-05-09 | Ananya
19 | RMS Live server update / back to list options are automatically taking to the UAT server | 2017-05-09 | Ananya
20 | Other Contract - Delete | 2017-05-09 | Ananya
21 | Author Codes and SAP Agreement numbers | 2017-05-09 | Ananya
22 | Executive / Manager creation not working | 2017-05-09 | Ananya
23 | Home Page changes after discussion with Bindu | 2017-05-10 | Ananya
24 | In permissions in-bound update mode not getting option to change status of assets from Pending to Cleared | 2017-05-10 | Ananya
25 | File size for upload increased to 20 MB from 2 MB | 2017-05-10 | Ananya
26 | Rights Selling contract expiry alert on dashboard | 2017-05-10 | Ananya
27 | Subsidiary rights entered not visible in Assignment Contract | 2017-05-10 | Ananya
28 | Subsidiary if entered No - to be visible | 2017-05-10 | Ananya
29 | Email upload not working | 2017-05-19 | Ananya
30 | Series Contract entry - Price and currency to be removed from Entry screen | 2017-05-19 | Ananya
31 | Payment tagging search - Add action link for more payments | 2017-05-19 | Ananya
32 | Series Product entry screen - dut to space issue - ISBN field removed from entry | 2017-05-19 | Ananya
33 | Series contract view not available on dasboard - to be shown on dasboard | 2017-05-19 | Ananya
34 | PAN no to be made PAN | 2017-05-22 | Ananya
35 | Permissions Outbound / Rights Selling - Translated spelling to be corrected | 2017-05-22 | Ananya
36 | Permissions Outbound / Rights Selling - Adapted spelling to be corrected | 2017-05-22 | Ananya
37 | Permissions Outbound / Rights Selling - Request material to be Requested material | 2017-05-22 | Ananya
38 | Permissions Outbound / Rights Selling - Invoice no. to be Invoice number | 2017-05-22 | Ananya
39 | Subsidiary if entered 0% for author and 100% for OUP should be visible | 2017-05-22 | Ananya
40 | Nominee details should not be mandatory | 2017-05-22 | Ananya
41 | Change in Product Category in Update mode not working | 2017-05-22 | Ananya
42 | Option to View Product License in List of Product Licenses expiring or expired | 2017-05-22 | Ananya
43 | Word Count in Subject Matter and Treatment to be increased to 5000 words | 2017-05-22 | Ananya
44 | Add Option to Delete Product from Admin log in | 2017-05-23 | Ananya
45 | Delete Contract Scan not working | 2017-05-23 | Ananya
46 | Assignment Contract Search - Project Handled by in disabled mode - to be updated | 2017-05-23 | Ananya
47 | Linked Products not searchable by child ISBN | 2017-05-23 | Ananya
48 | Product License alert on Home Page not re-directing | 2017-05-24 | Ananya
49 | Error in updating Product from Admin login | 2017-05-24 | Ananya
50 | Expiry date is visible on search but once we open the product it is not visible | 2017-05-24 | Ananya
51 | Expiry date error corrected - Agreement date missing | 2017-05-25 | Ananya
52 | Adaptation assignment contract - In request page Agreement date and Expiry date of license not visible | 2017-05-25 | Ananya
53 | Adaptation assignment contract - In request page Agreement date not visible after correction of above error | 2017-05-25 | Ananya
54 | Duplicate entry while tagging payment | 2017-05-26 | Ananya
55 | Permissions outbound payment tagging has Rights Selling as header | 2017-05-26 | Ananya
56 | Instrument Number to be a free text instead of numeric | 2017-05-26 | Ananya
57 | SAP Agreement numbers display - commas to be deleted | 2017-05-26 | Ananya
58 | Permission Inbound: If status is Cleared and fee is zero then it show as Gratis | 2017-05-26 | Ananya
59 | Assigmnent Contract - Document upload from Rights limited to one - Update mode to be provided to Rights for updating as many documents as required | 2017-05-26 | Ananya
60 | Assigmnent Contract - Author name not visible in Subsidiary rights field while doing Assignment contract entry | 2017-05-26 | Ananya
61 | Contract Expiry date to to be entry field and not to be calculated in Months | 2017-05-30 | Ananya
62 | Addendum Screen changes | 2017-05-29 | Ananya
63 | Proprietor company data not updated after corrections | 2017-05-29 | Ananya
64 | Proprietor company master not working in Edit mode | 2017-05-29 | Ananya
65 | Territory master not working | 2017-05-29 | Ananya
66 | Scanned document upload not working - showing error | 2017-05-29 | Ananya
67 | Royalty not visible after update | 2017-05-29 | Ananya
68 | Subsidiary rights royalty not visible after update | 2017-05-29 | Ananya
69 | Publisher in Publishing Company Master not working in Edit mode | 2017-05-29 | Ananya
70 | Publishing Company changed to Proprietor throughout system | 2017-05-29 | Ananya
71 | Error in Contributors name entry - can't delete additional row. | 2017-05-31 | Ananya
72 | If we are deleting any document then it is creating blank entry after submission. | 2017-06-01 | Ananya
73 | Permissions Inbound Update available only from Admin login - to be moved to Rights login | 2017-06-01 | Ananya
74 | Email upload in Ammendment to Standard Contract field not working | 2017-06-05 | Ananya
75 | Edition is open text field while doing Entry but Numeric if opened in Update mode. Change to Numeric in Entry mode | 2017-06-06 | Ananya
76 | Author copies made mandatory | 2017-06-06 | Ananya
77 | Corrected spelling of Teacher's manual | 2017-06-06 | Ananya
78 | Series contract update not working from Admin login | 2017-06-06 | Ananya
79 | Linked Products - Delink option not available | 2017-06-06 | Ananya
80 | Agreement search via SAP numbers not working | 2017-06-07 | Ananya
81 | Book to be removed from under Product Sub-type | 2017-06-07 | Ananya
82 | Manuscript delivery format alignment issue | 2017-06-09 | Ananya
83 | Duplicate contract details on permissions outbound screen | 2017-06-09 | Ananya | Open
84 | Permissions outbound - Number of copies to be disabled if No | 2017-06-09 | Ananya
85 | Permissions Outbound - Not showing subsidiary rights royalty percentage as defined at assignment contract screen | 2017-06-09 | Ananya
86 | If Invoice Applicable is No then Payment received should be default Not Applicable | 2017-06-09 | Ananya
87 | Licensee name search - Partial name search not working | 2017-06-09 | Ananya
88 | In Linked Products after linking with agreement, system is still showing Agreement not entered | 2017-06-19 | Ananya
89 | Issue with IE / Chrome | 2017-06-19 | Ananya
90 | Payment Tagging Entry to be changed to Enter Payment Details | 2017-06-19 | Ananya
91 | While entering Payment details - system is showing 2 entry boxes - one with author code and one without | 2017-06-20 | Ananya
92 | Change View Rights Selling to View Rights Sales Contract or View Contract | 2017-06-21 | Ananya
93 | Licensee Master -Change Mobile to Telephone number | 2017-06-21 | Ananya
94 | Add search option with Rights Sales ID | 2017-06-21 | Ananya
95 | URL for Licensee is updated in the Licensee Master but not showing while doing contract entry | 2017-06-21 | Ananya
96 | Change "Will be material be translated" to "Will the material be translated" | 2017-06-21 | Ananya
97 | Rights Sales View - Contract date to be changed to date of agreement from date of entry | 2017-06-21 | Ananya
98 | Rights Sales contract - Remarks entered not visible after submission | 2017-06-21 | Ananya
99 | Payemnt tagging - One entry is getting replicated multiple times | 2017-06-21 | Ananya
100 | Payment tagging - Author / OUP Statement - Print option not working | 2017-06-21 | Ananya
101 | Permissions Outbound and Rights Sales – Rename Payment Tagging to Payment Information | 2017-06-21 | Ananya
102 | Series contract - One correct entry - 2 additional contract entries created by system with partial data | 2017-06-21 | Ananya
103 | Permissions Outbound and Rights Sales – please rename Payment Tagging to Payment Information | 2017-06-22 | Ananya
104 | Same issue like we had in Rights Sales – 2 boxes for entering details – one with author code and one without | 2017-06-22 | Ananya
105 | Payment tagging screen here should not pick Invoice value. To make this an open field like in case of Rights Sales | 2017-06-22 | Ananya
106 | Permissions Outbound - If Invoice Applicable is ‘No’ then the Date of Invoice field should not come | 2017-06-22 | Ananya
107 | Permissions Outbound If Invoice Applicable is ‘No’ then Payment Received should not come as an option here (although it is disabled) | 2017-06-22 | Ananya
108 | Permissions Outbound - Remove ‘Mobile’ from the Telephone number field | 2017-06-22 | Ananya
109 | Screen is titled Pending Request for Permission Outbound’ – even after it has been update - To be corrected | 2017-06-22 | Ananya
110 | Terriroty Master - Slow upload | 2017-06-23 | Ananya | Open
111 | Product License entry error | 2017-06-27 | Ananya | Open
112 | Proprietor Company - edit mode issue | 2017-06-27 | Ananya
113 | Number of products in Series contract - View issue (Pagination) | 2017-06-30 | Ananya
114 | Upon data submission - 2 series contracts created | 2017-06-30 | Ananya
115 | Contract update data and scans visible when viewing Series Contract but not visible when viewing individual contract in the series | 2017-06-30 | Ananya
116 | Series product listing view is different from nomal Product Listing view. To make these similar and add Status, product category, etc | 2017-07-03 | Ananya
117 | Series contract - Page Upload issue - Taking too long after submission | 2017-07-03 | Ananya
118 | Series Contract View - Add Product Code and ISBN | 2017-07-03 | Ananya
119 | Duplicate licensee code removal | 2017-07-07 | Deepika
120 | Licensee code details not reflecting on Rights Sales and Outbound Permission Screen | 2017-07-07 | Deepika
121 | Site showing as Insecure | 2017-07-10 | Deepika | Ankush: For that install SSL on your system, please contact your IT team
122 | Rights Sales: - Unable to fill print run range in the royalty slab. It’s showing the last copies should be blank while it has be some numbers in most of the cases | 2017-07-10 | Deepika
123 | License Entry Error: Unable to do license entry. Error message "There is some problem". | 2017-07-13 | Ananya | Open
124 | Permission Inbound: for each asset entry one need to complete the entire process: go to Inbound/New/By Assignment Contract/Search the product/Product Name/Action/Add Permission Inbound and then Click Others (this is time consuming and there should be option of adding more assets for a title). | 2017-07-13 | Manoj | Open
125 | Permission inbound update : Though the copyright holder is populated in permission inbound page and while status of permission is being changed from pending to cleared , the following error message pops up, "PLEASE SELECT COPYRIGHT HOLDER". | 2017-07-13 | Manoj | Open
126 | Other Contract Entry: Tired entering and creating vendor record for 123RF but unable to do it. Error message pops up as, "There is an Error. Please try again". | 2017-07-14 | Manoj
127 | Permission Inbound: Unable to upload image permission log. | 2017-07-14 | Manoj | Open
128 | Series Not visible into RMS. The series Foundation of IT is not visible under assignment contracts. | 2017-07-17 | Navin | Open
129 | Right Sales: Replace number of impression with "First Publication Date" (Date format: dd/mm/yyyy ) | 2017-07-19 | Deepika
130 | Right Sales: Replace Seed Money with "Proprietor Copies" (this field would contain numbers) | 2017-07-19 | Deepika
131 | Other Contract - Please change the term ‘Party’ to ‘Vendor’ across | 2017-07-19 | Ananya | Open
132 | Other Contract - A tab capturing the Payment amount to be added under ‘Contract Details’ if Payment is Yes (Non-mandatory) | 2017-07-19 | Ananya / Siladitya | Open
133 | Other Contract - ‘Upload Contract’ nomenclature while doing the entry to be changed to ‘Upload Document’ (Non-mandatory) | 2017-07-19 | Ananya / Siladitya | Open
134 | Other Contract - ‘Other Contract Division Details’ should be on the top of the ‘Other contract view’ Screen | 2017-07-19 | Ananya / Siladitya | Open
135 | Other Contract - Other Contract Division Details’ to be renamed to ‘Division’ | 2017-07-19 | Ananya / Siladitya | Open
136 | Other Contract - Contract Issued by Executive’ to be changed to ‘Contract handled by’ | 2017-07-19 | Ananya / Siladitya | Open
137 | Other Contract - Even after updating the contract the tab is titled – ‘Pending Request for Other Contract’. Please correct this. | 2017-07-19 | Ananya / Siladitya | Open
138 | Other Contract - Shared list of 'Sevice' and 'Sub-service' to be added | 2017-07-19 | Ananya / Siladitya | Open
139 | ISBN bin not getting uploaded | 2017-07-19 | Ananya | Open
140 | Periodic contract expiry date not working - cannot update contract | 2017-07-19 | Ananya | Open
141 | Dashboard view issue - all updated contracts are not reflecting (Draft, Issued) | 2017-07-19 | Siladitya | Open
142 | Dashboard view issue - Pending for validation to be under one tab and Draft / Issued move to other tab - Ankush to correct this flow | 2017-07-19 | Ananya | Open
143 | Complete title search not working due to apostrophe in title | 2017-07-19 | Siladitya | Open
144 | Terminology to be standardiesd - change Licensor to Proprietor | 2017-07-19 | Ananya | Open
145 | Latency issue - worst are territory master and Series contracts | 2017-07-19 | Navin | Open
146 | Linked product ISBN - update issue | 2017-07-19 | Navin | Open
147 | Unable to update Author master due to nominee details. Please delete default data entered from Nominne | 2017-07-19 | Deepika | Open
148 | Errors - Please define type of error - currently system message says 'There is some error' | 2017-07-19 | Deepika | Open
149 | Double contracts reflecting - Product Code - PO5359 | 2017-07-19 | Siladitya | Open
150 | Licensee - Add search tab instead of drop down list (Outbound, Rights Selling) | 2017-07-19 | Deepika | Open
151 | Rights Sales - Add field for 'First Publication Date' | 2017-07-19 | Deepika | Open
152 | Rights Sales - Delete Organization Name column from Report | 2017-07-19 | Deepika | Open
153 | Permission Inbound - Copyright names are in alphabetical order when entering new, but not in alphabetical order when in update mode | 2017-07-19 | Manoj | Open
154 | Permission Inbound - Search with sub-product to be added. Currently it is only Product | 2017-07-19 | Manoj | Open
155 | Workflow change - Permissions Inbound / Impression entry | 2017-07-19 | Ananya | Open
156 | KIT ISBN | 2017-07-19 | Ananya | Open
157 | Add ISBN converter | 2017-07-19 | Ananya | Open